|  | 35 |
| --- | --- |
| Meeting Title: | Neighbourhood Plan Working Group |
| Date: | 4th January 2018 |
| Venue: | Village Hall, Holwell |
| Attendees: | Sally-Anne Holt (Chair Holwell Neighbourhood Plan Working Group) Steve Atchison Patrick Constable Colin Evans Dave Hollex Roger Kellow Neil Peirson Bruce Duncan (Chair Holwell Parish Council) Jo Witherden (Dorset Planning Consultant) |  | SAH SA PC CE DH RK NP BD JW |
| Agenda: | Part 1 - SAH Chair 1. Apologies for absence 2. Opening remarks 3. Declarations of Interest 4. Acceptance of notes from previous meeting 34 5. Actions arising from previous meetings Part 2 - JW & BD Chair 6. Review of data from NPWG members on each of the 24 Site Profiles to decide whether there are: - any material/significant changes that need to be made to the contents of any profile or - any listed buildings or heritage assets that have not been considered in the review of each site Agree outcomes Part 3 - SAH Chair 7. Site Options Consultation – update on checking with Electoral Roll 8. Update on further AECOM report 9. Update on Locality funding programmes 10. Update on draft Plan 11. Date of next meeting 12. AOB |  |  |

|  |  | Actions |
| --- | --- | --- |
| 1. | # Apologies |  |
|  | Lord Aldenham (LA), Rodney Antell (RA), Phil Curtis (PC), Jo Edmondson (JE), Di Gibbs (DG), Peter Mcfarlane (PM), and Libby Wilton (LW) were unable to attend. |  |
| 2. | Opening Remarks |  |
|  | SAH explained that the intention is to complete the Neighbourhood Plan this year. It was then explained that the format for this evening was to have SAH chair items 1 to 5 and 7 to 12, but item 6 would be chaired by JW and BD. |  |
| 3. | Declarations of Interest |  |
|  | There were declarations of interest from SAH, RK, CE and on behalf of Westbourne and Lotmead. |  |
| 4. | Notes Of Previous Meetings |  |
|  | The Notes for Meeting 34 were reviewed and accepted. |  |
| # 5. | # Actions Arising from Previous Meetings |  |
|  | # Meeting 34 Action 34-1: SAH has received 3 Declarations of Interest; she will send out a reminder for the others. Action 34-2: Action transferred to BD as this is a PC matter Action 34-3: Ongoing Meeting 35 Action 35-1: Being completed today. | SAH 35-1 |
| # 6. | # Review of Data from NPWG Members on Site Profiles |  |
|  | Eight sets of responses have been received by the new Clerk to the Parish Council, Sarah Mitchell. This feedback has been collated in a table with an entry for each of the sites being assessed. JW explained that the aim of this session is to go through this feedback and decide whether alterations to the assessment information is required, and if so whether the changes warrant further consultation. This process was completed. It was agreed that any interested parties in the group should take no part in the discussion of relevant properties, but did not need to leave the meeting. However, interested parties who also own the sites under discussion were obliged to leave the meeting and remain out of earshot until the discussion of that site was complete. |  |
| 7. | Site Options Consultation |  |
|  | SAH explained that we now have a total of 55 who have provided site assessment feedback and are on the Electoral Roll. She proposed that we have a meeting on the 18th January to review the results, with the aim of having open consultation in February, together with a draft plan. |  |
| 8. | AECOM Report |  |
|  | SAH explained that more funding has been granted for AECOM to look at design styles. NP pointed out that there are still inaccuracies in the AECOM report: SAH said that we cannot change this now. We can include it, or refer to it, and it could be available on line. |  |
| 9. | Update on Locality Funding |  |
|  | SAH explained that Locality funding ended at the end of December 2017. We need to produce a report and we can apply for more funding after March 2018. |  |
| 10. | Update on Draft Plan |  |
|  | The draft plan is progressing, and the main body of the draft report is now 35 pages long. |  |
| 11. | Dates of Next Meeting (DONM) |  |
|  | Date agreed as Thursday 18th January 2018, in the Village Hall. |  |
| 12. | Any Other Business (AOB) |  |
|  | SAH asked BD for progress on the website and he responded that there may be new individuals who can help with the NP website; the current site needs updating. BD pointed out that the Terms of Reference for the new Clerk to the Parish Council do not include support for the Neighbourhood Plan. SAH added that we are not in a position to pay at present but that she did not see a need for further support at this stage. CE asked about the recent issues that have arisen about the Shillingstone Neighbourhood Plan and a recent planning application. JW said that the application did not conform to the site specific policy of their Neighbourhood Plan, and was ultimately refused. CE asked if we could get planning decisions outside the Neighbourhood Plan limits. JW believed others may come forward, but that any market value housing should come under the plan. NP asked if our Neighbourhood Plan would carry any weight, before it reaches the examination stage. JW said probably not - data may be used but not policy. |  |